## Pending_Decisions
Pending Business Decisions
Release v1.0.0-rc1 ¦ Must be resolved before PASS status
Decision ID | Area | Current Proposed Value | Decision Required | Recommended Option | Business Owner | Finance Owner | Required Evidence | Status | Target Date | Final Decision | Approval Date | Remarks
PBD-01 | Margin Risk Thresholds | Normal <= 1pp, Warning <= 3pp, High Risk <= 5pp, Blocked > 5pp | Are these thresholds appropriate for all chains and categories? | Keep current values as starting point; review after 3 months of data |  |  | Historical margin change analysis by chain | PENDING | 2026-08-31
PBD-02 | GST Severity Rules | Blank GST = WARNING, Invalid GST = FAIL, Mismatch with Article Master = BLOCKED | Should blank GST be WARNING or FAIL? Should mismatch be BLOCKED or FAIL? | Keep current: WARNING for blank (may be filled later), BLOCKED for mismatch |  |  | GST audit trail from Finance | PENDING | 2026-08-31
PBD-03 | GST Article Master Cross-Check | GST rate validated against Article Master GST table when available | Should GST mismatch with Article Master always block the record? | Yes — GST errors have compliance implications |  |  | Finance confirmation | PENDING | 2026-08-31
PBD-04 | Margin Floor | Minimum margin = 0% (negative margins blocked) | Can any chain legitimately have a negative margin (e.g., promotional)? | Block negative margins; handle promotions via Consumer Offer % field |  |  | Commercial policy on negative margins | PENDING | 2026-08-31
PBD-05 | Margin Ceiling | Maximum margin = 100% | Is 100% the correct ceiling? Any category with different limits? | Keep 100% — margins above 100% are always data errors |  |  | None required (standard) | CONFIRMED |  | 100% |  | Standard business rule
PBD-06 | Approval Owners | Not yet assigned | Who submits, reviews, approves (commercial), approves (finance)? | Assign by chain group or category; at minimum one commercial + one finance |  |  | Organization chart and RACI | PENDING | 2026-08-15 |  |  | Must be filled before production
PBD-07 | Forecast Elasticity | Price elasticity = -1.2, Pass-through = 0.0, Inventory weeks = 4 | Are these elasticity values appropriate for Honasa/Mamaearth MT? | Start with pass-through = 0 (margin changes not passed to consumer price) |  |  | Demand Planning historical analysis | PENDING | 2026-09-30 |  |  | Low urgency — only affects forecast estimates
PBD-08 | Listing Eligibility | Only ACTIVE articles enter forecast-ready output | What listing statuses should be forecast-eligible? | ACTIVE only; delisted and discontinued should not feed forecast |  |  | Commercial listing policy | PENDING | 2026-08-31
PBD-09 | Alert Recipients | Not yet assigned | Who receives each alert severity? CRITICAL, HIGH, MEDIUM, LOW, INFO? | CRITICAL/HIGH: MT Head + Commercial; MEDIUM: MT Analyst; LOW/INFO: dashboard only |  |  | Distribution list from MT Head | PENDING | 2026-08-15
PBD-10 | Refresh Frequency | Monthly (Day 1-4 cycle as per SOP) | Is monthly sufficient? Any chain that requires weekly or ad-hoc? | Monthly for regular cycle; allow ad-hoc for emergency changes |  |  | Commercial team feedback | PENDING | 2026-08-31
PBD-11 | Retrospective Approval | Not currently supported | Can a margin change be approved retroactively after its effective date? | Allow with Finance dual-approval and documented justification |  |  | Finance audit policy | PENDING | 2026-09-30
PBD-12 | Emergency Approval | Not currently supported | Is an emergency fast-track approval process needed? | Yes — allow single-approver bypass for <= 1pp changes with post-hoc review |  |  | Commercial Head approval | PENDING | 2026-09-30

## Summary
Pending Decisions Summary
Total Decisions | 12
Confirmed | 1
Pending | 11
Release Gate | BLOCKED until PBD-06 (Approval Owners) and PBD-09 (Alert Recipients) resolved
Priority 1 (before go-live) | PBD-01, PBD-02, PBD-03, PBD-04, PBD-06, PBD-08, PBD-09, PBD-10
Priority 2 (within 30 days) | PBD-07, PBD-11, PBD-12
Already confirmed | PBD-05