## Known_Limitations
# | Limitation | Impact | Workaround | Priority | Target Resolution
1 | No real-data pilot completed yet | Business rules not validated against actual chain margin files | Run pilot with one real file before production use | P1 | Before production deployment
2 | Approval workflow is field-level only | No enforced state machine for DRAFT → APPROVED transitions | Manual review of Approval_Status field; add workflow enforcement in Phase 2 | P2 | Phase 2
3 | Impact analysis requires external NSV/volume driver | Rupee impact cannot be computed without Monthly_NSV input | Provide drivers DataFrame when calling impact_from_changelog() | P2 | When NSV data available
4 | No GUI / web interface | All operations via CLI or Python API | Use cli.py commands; consider Streamlit or Flask UI in Phase 2 | P3 | Phase 2
5 | No multi-user concurrent write protection | Simultaneous imports from different users could conflict | Coordinate imports sequentially; add file locking in Phase 2 | P2 | Phase 2
6 | Header alias mapping is manually maintained | New source file layouts may have unmapped headers | Add new aliases to schema.py HEADER_ALIASES dict | P3 | Ongoing
7 | Search is keyword-based, not NLP | Complex queries may not parse correctly | Use specific keywords: chain names, 'margin below X', category names | P3 | Phase 3
8 | No automated schedule for imports | Imports must be triggered manually | Use cron/task scheduler to call cli.py import on a schedule | P3 | Phase 2
9 | Business rule decisions pending | ~12 rules need business team confirmation before production | Complete Business_Rule_Register.xlsx sign-off | P1 | Before production deployment
10 | No email/notification on import completion | Users must check CLI output for import results | Add notification hook in Phase 2 | P3 | Phase 2