## TRACKER_SUMMARY
BUSINESS INPUT APPROVAL TRACKER — FY27 Forecast Engine ¦ Honasa / Mamaearth MT
Frozen commit: b08866f ¦ Freeze date: 2026-08-01 ¦ Generated: 2026-08-01 ¦ DO NOT run refresh_forecast.py until all P1 rows show APPROVED
LIVE APPROVAL DASHBOARD (auto-calculates from data below)
Total Inputs | ✓ Approved | ⏳ Pending | ✗ Blocked / Missing | P1 Items Not Approved | Safe to Run Forecast?
Input File | Business Owner | Reviewer | Due Date | Approval Status | Priority | Rows Available | Rows Approved | Coverage | Blocking Issue | Missing Fields | Comments
events_calendar.csv | Marketing + KAM | MT Head / Demand Planning | 2026-08-10 | PENDING_APPROVAL | P1 | 13 | 0 | 0 / 13 events approved | Forecast uses PLACEHOLDER uplifts — not business-approved | uplift_pct (all 13), conservative/base/stretch variants, approval_status | All 13 events PLACEHOLDER_TBC. Must approve before Aug forecast run.
launch_plan.csv | Category + Marketing | Supply Chain / Demand Planning | 2026-08-15 | SCHEMA_ONLY | P2 | 0 | 0 | No NPI rows | No NPI uplift applied — acceptable only if no NPIs planned | launch_month, chain_name, ean, initial_fill_qty, approval_status | Aug–Oct 2026 NPIs only. APPROVED rows only affect forecast.
targets.csv | Sales Planning + KAM | MT Head / Finance | 2026-08-08 | MISSING | P1 | 0 | 0 | No targets loaded | MOST CRITICAL — forecast cannot be compared to plan without this | month, chain_name, brand, article, ean, target_qty, target_nsv | Start with Aug–Oct 2026 at Chain × Brand × EAN grain.
fact_margin.csv (DERIVED) | Finance | Finance Controller | 2026-08-20 | PENDING_APPROVAL | P2 | 2113 | 0 | 0 / 2113 Finance-approved | CM2 reporting BLOCKED until Finance approves | cogs_per_unit, ba_cost_per_unit, visibility_cost_per_unit, approval_status=FINANCE_APPROVED | 2113 rows derived from offtake. Directional only — NOT Finance-approved.
fact_margin.csv (ESTIMATED) | Finance + Category | Finance Controller | 2026-08-20 | BLOCKED | P1 | 933 | 0 | 0 / 933 validated | 933 EANs carry placeholder MRP=250, margin=30%, cm2=15% | Real MRP, GST%, TOT%, margin_pct, cogs_per_unit per EAN | Primary-only EANs not in offtake. All values are estimates.
fact_margin.csv — DATA ISSUE | MDM / Finance | Finance Controller | 2026-08-08 | BLOCKED | P1 | 2 | 0 | VMM chain, 2 rows | 2 rows with negative margin_pct = -84.64 (likely credit memo / return) | EANs: 8904417314298, 8904417312546 — Rice Dewy Bright Face Wash, Vitamin C Face Wash | Reclassify as return record or exclude from margin master.
primary_history.csv | SAP / Data Team | Demand Planning | COMPLETE | APPROVED | — | ~35k | ~35k | FY27 Apr–May 2026 ✓ | None | None | Assembled and validated. Grain: month × chain_name × ean.
offtake_history.csv | Distributor / Ops | Demand Planning | COMPLETE | APPROVED | — | ~9.7k | ~9.7k | Apr–May 2026 (2 months only) | Only 2 months limits YoY backtesting | More months needed for YoY trend accuracy | 5 unmapped EANs remain — see UNMAPPED_EANS sheet.

## EVENTS_APPROVAL
EVENT UPLIFT APPROVAL — FY27 ¦ Yellow = business fills ¦ Formula cols auto-validate
RULE: Engine uses base_pct from col I for production. Provide all three: Conservative (H), Base (I), Stretch (J). Set approval_status (col L) = APPROVED only after business sign-off. Validation (col S) auto-checks all required fields are filled.
event_name | event_type | forecast_month | chain_filter | brand_filter | article_filter | current_uplift_pct (PLACEHOLDER) | conservative_pct ◀ fill | base_pct ◀ fill — used in forecast | stretch_pct ◀ fill | basis (Historical / Plan / Estimate) ◀ fill | approval_status ◀ set APPROVED after sign-off | approved_by | approved_date | business_owner | reviewer | due_date | comments | VALIDATION (formula)
Independence_Day | national_holiday | 2026-08 | ALL | ALL | ALL | 10.0 |  |  |  |  | PENDING_APPROVAL |  |  | Marketing / KAM | MT Head | 2026-08-10 | Patriotic buying surge — Aug 15
Raksha_Bandhan | festival | 2026-08 | ALL | ALL | ALL | 15.0 |  |  |  |  | PENDING_APPROVAL |  |  | Marketing / KAM | MT Head | 2026-08-10 | Gifting season — approx Aug 29 2026
Navratri | festival | 2026-10 | ALL | ALL | ALL | 20.0 |  |  |  |  | PENDING_APPROVAL |  |  | Marketing / KAM | MT Head | 2026-08-10 | Nine nights — approx Oct 6-14 2026
Dussehra | festival | 2026-10 | ALL | ALL | ALL | 15.0 |  |  |  |  | PENDING_APPROVAL |  |  | Marketing / KAM | MT Head | 2026-08-10 | Vijayadasami — approx Oct 15 2026
Big_Billion_Days | ecommerce_sale | 2026-10 | ALL | ALL | ALL | 25.0 |  |  |  |  | PENDING_APPROVAL |  |  | Marketing / KAM | MT Head | 2026-08-10 | Flipkart annual sale — approx Oct 7-11 2026
Great_Indian_Festival | ecommerce_sale | 2026-10 | ALL | ALL | ALL | 25.0 |  |  |  |  | PENDING_APPROVAL |  |  | Marketing / KAM | MT Head | 2026-08-10 | Amazon annual sale — approx Oct 7-11 2026
Diwali | festival | 2026-11 | ALL | ALL | ALL | 35.0 |  |  |  |  | PENDING_APPROVAL |  |  | Marketing / KAM | MT Head | 2026-08-10 | Peak festive season — approx Nov 9 2026
Childrens_Day | national_holiday | 2026-11 | ALL | ALL | ALL | 5.0 |  |  |  |  | PENDING_APPROVAL |  |  | Marketing / KAM | MT Head | 2026-08-10 | Minor uplift — Nov 14
Christmas | festival | 2026-12 | ALL | ALL | ALL | 15.0 |  |  |  |  | PENDING_APPROVAL |  |  | Marketing / KAM | MT Head | 2026-08-10 | Year-end gifting — Dec 25
New_Year | festival | 2027-01 | ALL | ALL | ALL | 20.0 |  |  |  |  | PENDING_APPROVAL |  |  | Marketing / KAM | MT Head | 2026-08-10 | New Year celebration — Jan 1 2027
Makar_Sankranti | festival | 2027-01 | ALL | ALL | ALL | 10.0 |  |  |  |  | PENDING_APPROVAL |  |  | Marketing / KAM | MT Head | 2026-08-10 | Harvest festival — Jan 14 2027
Republic_Day | national_holiday | 2027-01 | ALL | ALL | ALL | 8.0 |  |  |  |  | PENDING_APPROVAL |  |  | Marketing / KAM | MT Head | 2026-08-10 | National day — Jan 26 2027
Holi | festival | 2027-03 | ALL | ALL | ALL | 25.0 |  |  |  |  | PENDING_APPROVAL |  |  | Marketing / KAM | MT Head | 2026-08-10 | Spring festival — approx Mar 21 2027
APPROVAL PROGRESS (live formula summary)
Total Events |  |  | Approved |  |  | Pending |  |  | With base_pct filled |  |  | Events in Aug |  |  | Events in Oct

## TARGETS_TEMPLATE
TARGETS INPUT TEMPLATE — FY27 Aug–Oct 2026 ¦ MOST CRITICAL missing input
Required grain: Chain × Brand × EAN × Month. Where only chain-brand totals available, use target_source=ALLOCATED and allocation_method. Yellow = required. target_qty must be > 0.
month (YYYY-MM) | chain_name | brand | article | ean | target_qty (units) | target_nsv (₹) | target_primary_qty (units) | target_source (ACTUAL / ALLOCATED) | allocation_method (HISTORICAL / MGMT_ESTIMATE) | approved_by | quality_status (ACTUAL_BUSINESS_TARGET / ALLOCATED / MISSING) | VALIDATION (formula)
↓ EXAMPLE ROW — delete before uploading ↓
2026-08 | Apollo Pharmacy | Mamaearth | Onion Hair Oil 150ml | 8906087751234 | 500 | 75000 | 600 | ACTUAL_BUSINESS_TARGET | N/A | Sheshant Aswal | ACTUAL_BUSINESS_TARGET
LIVE SUMMARY (auto-calculates as you add target rows)
Rows entered |  | Valid rows |  | Rows with issues |  | Total target_qty |  | Total target_nsv |  | Months covered

## NPI_TEMPLATE
NPI LAUNCH PLAN — Aug–Oct 2026 only ¦ Only APPROVED rows affect forecast
Month 1 = initial fill + launch demand. Month 2 = distribution expansion. Month 3 = normalized run rate. After ramp-up, engine switches to trend-based. Yellow = required. Only APPROVED rows affect production.
launch_month (YYYY-MM) | chain_name (or ALL) | brand | article | ean | launch_type (NATIONAL/REGIONAL/CHAIN_EXCLUSIVE) | planned_stores | expected_distribution_pct (%) | initial_fill_qty | monthly_run_rate_qty | ramp_up_months (1-3) | month_1_uplift_pct | month_2_uplift_pct | month_3_uplift_pct | owner | approval_status ◀ APPROVED / PENDING | remarks | VALIDATION (formula)
↓ EXAMPLE ROW — delete before uploading ↓
2026-08 | ALL | Mamaearth | New Vitamin C Serum 30ml | 8906087799999 | NATIONAL | 850 | 65 | 12000 | 8000 | 3 | 80 | 90 | 100 | Category Mgr | PENDING | Awaiting trade plan
LIVE NPI SUMMARY
NPIs entered |  |  | Approved |  |  | Pending |  |  | Total initial fill |  |  | Approval rate

## MARGIN_STATUS
MARGIN REPOSITORY STATUS ¦ CM2 reporting BLOCKED until Finance sets approval_status = FINANCE_APPROVED
DERIVED = computed from offtake (directional, not Finance-approved). ESTIMATED = placeholder MRP ₹250, margin 30%, cm2 15% — must be replaced with real Finance data. Negative margin_pct = data quality issue — must be resolved before CM2 reporting.
quality_status | count_rows | count_eans | count_chains | avg_mrp (₹) | avg_margin_pct (%) | avg_cm2_pct (%) | negative_margin_rows | approval_status_required | owner
DERIVED | 2113 | 507 | 25 | ₹21597 | 44.2% | 2591.6% | 2 | FINANCE_APPROVED required | Finance Controller
ESTIMATED | 933 | 933 | 1 | ₹250 (PLACEHOLDER) | 30.0% | 15.0% | 0 | REPLACE WITH REAL DATA — BLOCKED | Finance + Category
DATA QUALITY ISSUES — must resolve before Finance sign-off
ean | chain | brand | article | month | mrp | margin_pct | issue_type | recommended_action | owner
8904417314298 | VMM | Mamaearth | Rice Dewy Bright Face Wash | 2026-04 | 750 | −84.64 | NEGATIVE_MARGIN | Reclassify as return/credit memo or exclude from master | MDM / Finance
8904417312546 | VMM | Mamaearth | Vitamin C Face Wash 150 ml | 2026-04 | 562.5 | −84.64 | NEGATIVE_MARGIN | Reclassify as return/credit memo or exclude from master | MDM / Finance
REQUIRED FULL MARGIN SCHEMA — provide to Finance for export
column_name | format | required | owner | current_status
month | YYYY-MM | REQUIRED | Finance | Present (DERIVED/ESTIMATED)
chain_name | text | REQUIRED | Finance | Present
ean | text | REQUIRED | Finance | Present
mrp | ₹ per unit | REQUIRED | Finance | Present — ESTIMATED rows = ₹250 placeholder
gst_pct | % | REQUIRED | Finance | MISSING
invoice_discount_pct | % | REQUIRED | Finance | MISSING
off_invoice_discount_pct | % | REQUIRED | Finance | MISSING
tot_pct | % | REQUIRED | Finance | Present (as tot_pct)
trade_margin_pct | % | REQUIRED | Finance | Present as margin_pct — name mismatch
cogs_per_unit | ₹ | REQUIRED | Finance | MISSING
claim_per_unit | ₹ | OPTIONAL | Finance | MISSING
ba_cost_per_unit | ₹ | OPTIONAL | Finance | MISSING
visibility_cost_per_unit | ₹ | OPTIONAL | Finance | MISSING
rental_cost_per_unit | ₹ | OPTIONAL | Finance | MISSING
cm1_pct | % | REQUIRED | Finance | MISSING
cm2_pct | % | REQUIRED | Finance | Present — ESTIMATED rows = 15% placeholder
approval_status | FINANCE_APPROVED / PROVISIONAL | REQUIRED | Finance Controller | MISSING
effective_from | YYYY-MM | REQUIRED | Finance | MISSING
effective_to | YYYY-MM or OPEN | REQUIRED | Finance | MISSING

## UNMAPPED_EANS
UNMAPPED EAN REGISTER ¦ 5 EANs in offtake not in margin master — resolve before UAT
ean | article_source_name | chain_name | months_seen | sales_qty | sales_nsv | issue_type | recommended_action | owner | status
Run audit — EAN slot 1 |  |  | Apr–May 2026 |  |  | OPEN — PENDING INVESTIGATION | Investigate & reclassify | MDM / Category | OPEN
Run audit — EAN slot 2 |  |  | Apr–May 2026 |  |  | OPEN — PENDING INVESTIGATION | Investigate & reclassify | MDM / Category | OPEN
Run audit — EAN slot 3 |  |  | Apr–May 2026 |  |  | OPEN — PENDING INVESTIGATION | Investigate & reclassify | MDM / Category | OPEN
Run audit — EAN slot 4 |  |  | Apr–May 2026 |  |  | OPEN — PENDING INVESTIGATION | Investigate & reclassify | MDM / Category | OPEN
Run audit — EAN slot 5 |  |  | Apr–May 2026 |  |  | OPEN — PENDING INVESTIGATION | Investigate & reclassify | MDM / Category | OPEN
To populate: python forecast_engine/data_readiness_audit.py → copy unmapped_eans from audit_output/audit_issues.csv
RESOLUTION PROGRESS
Total EANs |  | Resolved |  | Excluded |  | Still Open

## VALIDATION_CHECKLIST
PRE-REFRESH VALIDATION CHECKLIST ¦ Run: python validate_business_inputs.py --mode full
BLOCKED = Stop. Do not run forecast. FAIL = Fix before running. WARNING = Document and proceed with caution. Column H status auto-updates when you paste actual results in col G.
Check ID | File | Check Description | Severity | Validation Rule | Pass Criterion | Actual Result (paste after running) | Status (formula) | Notes
V-01 | targets.csv | At least one data row present | BLOCKED | Row count > 0 | ≥ 1 row for Aug–Oct 2026 |  |  | Most critical missing input. Upload Chain × Brand × EAN targets.
V-02 | targets.csv | No blanks in required columns | BLOCKED | No NaN in month, chain_name, brand, ean, target_qty | 0 blank required fields
V-03 | targets.csv | month format YYYY-MM | FAIL | regex \d{4}-\d{2} | All rows match
V-04 | targets.csv | No negative target_qty or target_nsv | FAIL | target_qty >= 0, target_nsv >= 0 | 0 negative values
V-05 | targets.csv | No duplicate month × chain × brand × ean | BLOCKED | Deduplication check | 0 duplicates
V-06 | targets.csv | No MISSING quality_status rows | FAIL | quality_status != MISSING | 0 MISSING rows
V-07 | events_calendar.csv | No PLACEHOLDER_TBC rows | BLOCKED | status = APPROVED only | 0 PLACEHOLDER_TBC rows |  |  | All 13 events currently PLACEHOLDER_TBC.
V-08 | events_calendar.csv | No overlapping events same chain × brand × month | FAIL | No dup forecast_month + chain + brand | 0 overlapping rows
V-09 | events_calendar.csv | uplift_pct between 0 and 100 | FAIL | 0 <= uplift_pct <= 100 | All rows within range
V-10 | events_calendar.csv | forecast_month format YYYY-MM | FAIL | regex \d{4}-\d{2} | All rows match
V-11 | launch_plan.csv | All NPI rows approval_status = APPROVED | BLOCKED | status = APPROVED only | 0 PENDING rows affect forecast |  |  | Empty file = PASS (no NPI uplift applied).
V-12 | launch_plan.csv | launch_month in YYYY-MM format | FAIL | regex \d{4}-\d{2} | All rows match
V-13 | launch_plan.csv | No negative uplift percentages | FAIL | month_N_uplift_pct >= 0 | 0 negative values
V-14 | fact_margin.csv | No ESTIMATED rows | BLOCKED | quality_status != ESTIMATED | 0 ESTIMATED rows |  |  | Currently 933 ESTIMATED rows — placeholder values.
V-15 | fact_margin.csv | approval_status column present | FAIL | Column exists | Column found |  |  | Add approval_status column; Finance marks FINANCE_APPROVED.
V-16a | fact_margin.csv | No negative mrp | FAIL | mrp > 0 | 0 negative MRP rows
V-16b | fact_margin.csv | No negative margin_pct | FAIL | margin_pct >= 0 | 0 negative rows |  |  | Currently 2 negative rows (VMM chain) — see MARGIN_STATUS sheet.
V-16c | fact_margin.csv | No negative cm2_pct | FAIL | cm2_pct >= 0 | 0 negative rows
V-17 | fact_margin.csv | No duplicate month × chain × ean | BLOCKED | Deduplication check | 0 duplicates |  |  | Currently 0 duplicates ✓
V-18 | fact_margin.csv | mrp > 0 for all rows | FAIL | mrp > 0 | 0 zero-MRP rows
V-19 | cross-file | All target EANs exist in fact_margin | FAIL | EAN cross-reference check | 0 unmapped EANs
V-20 | all files | No excluded brands (Pure Origin, Lumineve, Staze) | BLOCKED | brand NOT IN excluded list | 0 excluded brand rows |  |  | Hard rule — never appears in forecast.
V-21 | offtake_history.csv | 0 unmapped EANs (5 currently open) | WARNING | Audit unmapped EAN register | All 5 EANs resolved |  |  | See UNMAPPED_EANS sheet.
V-22 | primary_history.csv | No duplicate month × chain × ean | BLOCKED | Deduplication check | 0 duplicates (currently 0 ✓)
OVERALL GATE RESULT (live formula — auto-updates when col G is filled)
Checks run | PASS | REVIEW | PENDING | BLOCKED | FAIL count | Warnings |  | OVERALL STATUS

## COMMANDS_REFERENCE
COMMAND REFERENCE ¦ Exact commands to run at each stage
Stage | Command | Expected Output / Pass Criterion | Notes
STEP 1 Unit tests (any time) | python -m forecast_engine.selftest | Ran 20 tests in ~0.04s OK → Must be 20/20 | Run after any code change. Zero tolerance — 20/20 always.
STEP 2 Data readiness audit | python forecast_engine/data_readiness_audit.py --primary Phase_A_Input/primary_history.csv --offtake Phase_A_Input/offtake_history.csv --margin Phase_A_Input/fact_margin.csv | gate_status: PASS BLOCKED: 0 FAIL: 0 → Output: audit_output/audit_summary.json | Run after any Phase_A_Input file changes. BLOCKED > 0 = hard stop.
STEP 3 Business input validator | python validate_business_inputs.py --mode full # Write JSON report: python validate_business_inputs.py --mode full --out validation_results.json | RESULTS: PASS=22 WARNING=0 FAIL=0 BLOCKED=0 → Must see: safe to run refresh_forecast.py → Exit code 0 | Must clear ALL BLOCKED and FAIL before Step 4. Currently: BLOCKED=3 FAIL=2 — resolve business inputs first.
STEP 4 Production forecast | python refresh_forecast.py --months 3 --verbose | PRODUCTION_READY 9,138+ forecast records All 5 gates PASS/WARNING → Output: forecast_outputs/<run_id>/ | Only run after Steps 1–3 return all-clear. Do NOT run with BLOCKED or FAIL in Steps 1–3.
STEP 5 Verify event uplifts | python -c " import pandas as pd df = pd.read_csv('forecast_outputs/<run_id>/PowerBI/fact_demand_forecast.csv') print(df.groupby('forecast_month')['festival_uplift'].describe()) print('Rows with uplift>0:', (df['festival_uplift'].astype(float)>0).sum()) " | Aug: mean > 0 (Raksha Bandhan) Sep: mean = 0 Oct: mean > 0 (Big Billion / GIF) → Replace <run_id> with actual dir | Verify approved uplifts are being applied. festival_uplift > 0 for event months.
STEP 6 Warehouse reconciliation | python -c " import pandas as pd df = pd.read_csv('forecast_outputs/<run_id>/PowerBI/fact_demand_forecast.csv') for c in ['forecast_primary_qty','warehouse_gurgaon','warehouse_mumbai','warehouse_bangalore','warehouse_kolkata']: df[c] = pd.to_numeric(df[c], errors='coerce').fillna(0) df['wh_sum'] = df[['warehouse_gurgaon','warehouse_mumbai','warehouse_bangalore','warehouse_kolkata']].sum(axis=1) mismatch = (df['forecast_primary_qty'] - df['wh_sum']).abs() print('Max mismatch:', mismatch.max(), '— rows:', (mismatch>0.1).sum()) " | Max mismatch: < 0.1 Rows with mismatch: 0 → Warehouse sum must equal forecast_primary_qty | Gate 5 already checks this; run manually to confirm.
STEP 7 Update evidence | # After a successful approved run: git add PHASE_A_VALIDATION_EVIDENCE.md git add BUSINESS_INPUT_APPROVAL_TRACKER.xlsx git commit -m 'chore: update validation evidence — [run_id]' git push -u origin <branch> | Evidence file and tracker pushed to branch | Update PHASE_A_VALIDATION_EVIDENCE.md with new run details. Keep tracker current.
STEP 8 Backtesting (once ≥3 months offtake) | python forecast_engine/backtesting_framework.py Phase_A_Input backtest_output | WAPE Total MT ≤ 10% WAPE Chain ≤ 15% WAPE Chain × Brand ≤ 20% Forecast Bias within ±5% | Currently only 2 months of offtake (Apr–May 2026). Re-run when Jun 2026 offtake is loaded.