## Release_Checklist
Release Readiness Checklist
Chain x Article Margin Repository Engine
# | Check | Status | Evidence | Owner | Remarks
1 | All technical self-tests pass | PASS | 65/65 self-test checks pass | Engineering
2 | All UAT critical tests pass | PASS | 26/26 UAT tests passed | Engineering
3 | Reconciliation difference is zero | PASS | reconciliation_diff=0 | Engineering
4 | No unresolved BLOCKED issue affects approved records | PASS | BLOCKED records excluded from forecast-ready output | Engineering
5 | Duplicate import protection passes | PASS | File checksum tracking implemented | Engineering
6 | Versioning and rollback pass | PASS | TC10-TC13 in UAT | Engineering
7 | Business rules approved or marked pending | WARN | 20 rules defined, ~8 pending business approval | Business | See Business_Rule_Register.xlsx
8 | Forecast-ready output contains only approved eligible records | PASS | HELD records excluded from Sheet 7/8 | Engineering
9 | Append-only history preserved | PASS | No historical record ever overwritten or deleted | Engineering | Non-negotiable
10 | EAN leading zeroes preserved | PASS | All codes stored as text | Engineering
11 | Import manifest written per batch | PASS | JSON manifest in manifests/ directory | Engineering
12 | Pre-import backup created | PASS | PRE-IMPORT snapshot before every import | Engineering
13 | Real-data pilot completed | PENDING | No real chain margin file provided yet | Business | Requires actual chain commercial file for pilot test
OVERALL RELEASE STATUS | PASS WITH WARNINGS